## Summary
Coordinator:
IRB #
Summary
Item | Completed
Confidentiality Agreement (CDA)
Center for Clinical and Translational Science (CCTS)
Site Selection and Initiation
Clinical Trial Agreement (CTA)
Sponsor Budget Development/Negotiation
IDS
eIAF
Insurance Analysis
Conflict of Interest
Account Creation
Plan Code
Create regulatory binder
Protocol
Investigator Brochure
Study Start-up Packet to Sponsor
Draft Consent/HIPAA to Sponsor
IRB Submission
IRB Revisions
Initial IRB Approval
VA R&D
Markey Cancer Center Protocol Review Committee
Institutional Biosafety Committee (IBC)
Device Committee
Indemnification Committee
Home Health Exemption

## Checklist
Industry Sponsored New Study Checklist
Study Title:
Sponsor:
Investigator:
CRA:
Coordinator:
IRB #
| Date | Date
Item | Received | Completed | Comments
Confidentiality Agreement (CDA)
Most sponsors want a confidentiality agreement signed prior to sending the protocol. PIs are not authorized to sign off on CDAs. The Office of Technology and Commercialization is the only one with signatory authority on these. Ali Bocook is the contact. https://www.research2.uky.edu/office-technology-commercialization/material-transfers-and-confidential-disclosures
Sent CDA to Intellectual Property
Signed CDA back to sponsor
Fully executed CDA filed in reg binder
Center for Clinical and Translational Science (CCTS)
If utilizing the services of the Center for Clinical and Tranlational Science (CCTS) you need to complete a service request form at http://www.ccts.uky.edu/ccts/ccts-service-request-forms. The CCTS will contact you and provide a budget estimate sheet and letter of agreement for your project. These must be executed prior to initiation of services. Anyone that uses CCTS services must complete Good Clinical Practice training. See the link below.
Budget Estimate and Letter of Agreement Executed with CCTS (if applicable)
Site Selection and Initiation
Site Selection Letter filed in Reg Binder
Site Initiation Vist Scheduled
Clinical Trial Agreement (CTA)
Clinical Trial Agreements are negotiated by the Office of Sponsor Projects Administration (OSPA). PIs cannot sign off on CTAs. OSPA is the only signatory authority that can sign CTAs.
CTA sent to OSPA for negotiation
Fully Executed CTA
Coverage Analysis
Once coverage Analysis is complete, Budget development can start. Be sure to use the Analysis documents during development
Fill Out the CRSO Coverage Analysis Form and send required documents to crso@l.uky.edu
Coverage Analysis Determination received/filed
Sponsor Budget Development/Negotiation
Sponsors will typically send a budget template for PIs to use to assist with negotiating budgets. This is strictly a template and you should always prepare a budget using actual costs to help with negotiation. Along with patient care costs don't forget to include PI effort, coordinator effort, regulatory support, grants management support, IDS, ancillary costs, patient stipend, long-term storage costs, IRB fees, pass-thru costs (protocol amendments, SAEs, IND safety reports, protocol violations, etc), indirect costs, etc.
Sponsor budget template received
Budget Development being done by:
Estimate requested from IDS. Seth Larkin 218-5562. Send Protocol and estimated enrollment for this estimate (if applicable)
Sponsor approved budget
eIAF http://www.research.uky.edu/ospa/info/eiaf_training.html
Conflict of Interest Form completed for all Key personnel. http://www.research.uky.edu/ospa/coi.html
Plan code requested https://ukhealthcare.mc.uky.edu/compliance/research/default.aspx
CGS/CMS approval for devices (if applicable)
WBS Number
Plan Code
Regulatory
Sponsors will typically provide a list of regulatory documents needed to initiate the study and a regulatory binder to store the documents.
Create regulatory binder
Protocol
Copy to IDS (if applicable)
Copy to PI
Copy to sponsor budget developer
PI signed signature page
File in Reg binder
Investigator Brochure (if applicable)
Copy to IDS
Copy to PI
PI signed signature page (if applicable)
File in Reg binder
Study Start-up Packet to Sponsor
1572 signed by PI (if applicable)
CVs/Medical License filed in Reg binder
Collect CITI Human Subject Protection and Good Clinical Practice training certificates CITI Training: http://www.uky.edu/see/page/linkblue-subpage
Lab Normals/Certifications (all applicable). Print Lab Normals and CAP/CLIA from: http://www.hosp.uky.edu/ClinLab/geninfo.htm
IRB Membership Roster and FWA http://www.rgs.uky.edu/ori/human/IRBMembership.html
Sponsor's Financial Disclosures
Complete regulatory packet sent to sponsor
Draft Consent/HIPAA to Sponsor
Draft Consent/HIPAA to regulatory manager
Regulatory manager okayed for release to sponsor
Emailed to sponsor
Revisions Received
Revisions completed/Emailed back to sponsor
Sponsor's Approval
IRB Submission
IRB Consult
Complete e-IRB application
Forward for Department Chair and PI signature in e-IRB
Submission sent to IRB
IRB submission log updated
IRB meeting date/time e-mailed to PI by IRB
IRB Revisions
Revise e-IRB application as needed according to the IRB
Consent/Assent/HIPAA revisions sent to Sponsor
Sponsor approved revisions
Other IRB required Forms (if applicable)
Submit revisions in e-IRB
IRB submisison log updated
Initial IRB Approval
Approval documents faxed/emailed to sponsor
IRB submission log updated
Copy sent to budget/contract negotiator
Copy of consent(s) to coordinator
Hard copy documents filed in Reg binder
Additional Reviews (if applicable)
VA R&D https://www.lexington.va.gov/research/index.asp
Markey Cancer Center Protocol Review Committee (PRMC) http://ukhealthcare.uky.edu/Markey/PRMC/
Institutional Biosafety Committee (IBC) http://ehs.uky.edu/docs/pdf/bio_ibc_registration_0001.pdf
Device Committee - CMS/CGS
Indemnification Committee http://www.ccts.uky.edu/ccts/non-indemnification-clinical-study-rmc-approval-process
Home Health Exemption - If your study involves seeing patients/subjects in their homes, please contact UK legal at 323-1161 to determine if a Ky notice requirement applies to your study.
Note: Please consider filing your documents electronically as well as in your regulatory binder